## Sheet1
| February | March | April | May | June | July | August | September | October | November | Decemeber
Finalize design | bar: February
Main menu module | March: 1st half
Custom generated content | March: Last half
Start/Load Games | March: Last half
Player Control | April: 1st half
AI Behaviour | April: 1st half
Random generation and environments | April: Last half
Combat module | Decemeber: DEADLINE
Travel module | bar: May to August
Rest module | bar: May to August
Test phase 1 | bar: May to August
Final combat, endgame module | September: 1st half
Combine all modules, test phase 2 | bar: September to October
Implement networking (optional) | bar: October to November
Test phase 3 (if networking) | bar: October to November